**CMPS115 Sprint 2 Plan**

**Goal**

After the second sprint, it should be possible for administrators to remove bad content and for readers to be able to use the app on shaky connections. Readers will also be given various quality-of-life improvements.

**Task Listing**

**User Story 1** - As a reader, I would like to be able to search for specific comics so that I can

easily find content that interests me.

**Acceptance**: There must be a good looking UI element visible from the comics list view in which the user can enter a search query the list of comics must then be restricted to only those comics whose title or description contain that query.

* Build angular search service (2 hrs)
* Add search UI to comic list (4 hrs)

*Total Time - 6 hrs*

**User Story 2** - As a reader, I would like to be able to return to the last page I read so that I can

easily pick up where I left off.

**Acceptance**: The reader must remember what pages have been read and store this data between sessions they must then use this information to allow the user to skip to the latest page with either the entire comic or a chapter within the comic.

* Store read pages in IndexedDB (3 hrs)
* Write logic to skip to latest page of logical section (whole comic or chapter) (2 hrs)
* Modify UI with skip buttons for comic/chapter (2 hrs)

*Total Time - 7 hrs*

**User Story 3** - As a reader, I want the viewing experience to be smooth, even when my

connection is poor, so that I can read the comics with greater ease.

**Acceptance**: The reader should be able to load offline as a progressive web application. The comics list should display some information even before the ajax request finishes. Finally, the next few pages of a comic the user is browsing the user specifically requests them.

* Preload images next few pages (2 hrs)
* Store previous comic metadata/comic list then merge with new results from server (5 hrs)
* Add PWA Manifest (2 hrs)
* Ensure Service Worker installs correctly (3 hrs)

*Total Time - 12 hrs*

**User Story 4** - As an administrator, I want to be able to remove inappropriate content so that I can

maintain the integrity of the web comic viewer.

**Acceptance**: an administrator must be able to find users that have acted problematically, for example by being able to identify them from their comic. The backend must then ignore authentication tokens from banned users and prevent them from creating new accounts.

* Make backend separate user/admin role in the database (1 hr)
* Create backend route to delete a comic ( 3 hrs)
* Create UI for admins to delete a comic ( 3 hrs)

*Total Time - 7 hrs*

**User Story 5** - As an administrator, I want to be able to ban problematic account users so that I

can prevent repeat offenses from occuring.

**Acceptance**: An administrator must be able to discover inappropriate content and then cause a comic to be able to be deleted from the database.

* Make a attribute in the user table to mark a banned account (1 hr)
* Prevent users from logging in to banned accounts and rescind their authorization (tokens should be invalid) (3 hr)
* Create a route that marks an account banned (3 hrs)
* Build UI for an admin to ban a comics owner (3 hrs)

*Total Time - 10 hrs*

**User Story 6** - As an administrator, I want to be able to communicate issues with account

users so that they understand what violations they made.

**Acceptance**: The admin should have a view from which they can send messages and the user should receive a notification of the message and be able to read it.

* Create a table to store admin messages. (2 hrs)
* Create a route where admins can send messages. (3 hrs)
* Create a route where users can look up messages received. (3 hrs)
* Create UI for admins to send messages to users. (3 hrs)
* Create UI for users to receive messages. (3 hrs)

*Total Time - 14 hrs*

**Team Roles**

Will: Product Owner, Full-stack Dev

Myron: Backend Dev

Sammy: Backend Dev

James: Frontend Dev

Mehtab: Scrum Master, Backend Dev

Alan: Scrum Master, Full-stack Dev

**Initial Task Assignment**

Will: User story 3 - Add PWA Manifest (2 hrs)

Myron: User story 5 - Make a attribute in the user table to mark a banned account (1 hr)


Sammy: User story 4 - Create a backend route to delete comics (3 hrs)

James: User story 1 - Add search UI to comic list (4 hrs)

Mehtab: User story 1 - build Angular search service (2 hrs)

Alan: User story 2 - Store read pages in IndexedDB (3 hrs)

**Initial Burnup Chart**



# Scrum Times

Monday: 4:00-4:15

Tuesday: 4:10-4:25 - TA meeting

Thursday: 3:30-3:45